## Requirements
Name |  | Kim Charlotte Anicete
Client Name |  | MotorPH
REQUIREMENTS IDENTIFICATION
# | GUIDE QUESTIONS | ANSWER (Write your answer to the guide question based on your current understanding) | ITEMS FOR CLARIFICATION (Identify items you need to clarify with your mentor)
1 | What problem is the client trying to resolve or what business need are they trying to fulfill? | Have an end-to-end inventory and payroll system to manage the products, employee details, and salary in an effective and efficiently managed way.
2 | What are your assumptions about the requirement? | Regarding the conditions necessary to improve MotorPh's system, my assumptions are unambiguous and direct.
3 | What is the end goal for completing this? | The ultimate objective is to create a thorough inventory and payroll system that manages goods, personnel information, and compensation from start to finish in order to optimize processes, increase efficiency, and provide better outcomes for clients.
4 | What features are the client looking for? | Among these features is the capacity to display personnel data in a format that is prescribed, which should include the employee number, employee name, and birthdate. System should be able to calculate the number of hours an employee has worked in a given week and compute the gross weekly salary of an employee based on the hours worked. Additionally, generic deductions should be applied by the system in order to calculate an employee's net weekly compensation. Taxes, insurance premiums, and retirement contributions are just a few examples of the expenses that can be written off. The system will be able to give the client a precise and effective way to manage employee payroll and financial records by providing these functionalities.
5 | Are the features part of a process? Is yes, what are the steps? | The following processes are outlined in the client's requirements for a payroll and financial records management system: 1. Presentation of Personnel/Employee Information: - Presenting personnel information in a predetermined format. 2. Calculation of the Hours Worked: - Calculating weekly working hours. 3. Computation of Gross Weekly Salary: - Calculating the gross weekly salary by using the hours worked. 4. Application of Deductions - Incorporating generic deductions like taxes, insurance, and retirement payments. 5. Calculation of Net Weekly Salary: - Formulating the weekly net income of an employee after deductions When all of these procedures are done, an effective system for handling employee payroll and financial documentation is created.
6 | Do you have thoughts on how this feature can be developed differently? | Enhancements for improving the payroll and financial records management system: 1. Automation of Processes: - Implement automated payroll calculations, tax deductions, and benefit calculations to reduce errors and save time. - Automate data entry processes to minimize manual input, reducing the risk of human errors. 2. Integration with HR and Accounting Systems: - Ensure seamless integration with HR systems to streamline employee onboarding, changes, and offboarding processes. - Integrate with accounting software to facilitate easier financial reconciliation and reporting. 3. Real-Time Reporting and Analytics: - Provide real-time access to financial and payroll reports for better decision-making. - Implement analytics tools to identify trends, forecast expenses, and optimize financial strategies. 4. Time and Attendance Integration: - Integrate time and attendance systems to automate the tracking of hours worked, overtime, and leave balances. - Use biometric or other advanced technologies for accurate time tracking. 5. Enhanced Data Backup and Recovery: - Regularly back up payroll and financial data and implement a robust disaster recovery plan to ensure data integrity and availability.
7 | How will you know that the requirements have been completed? | The Project Plan and the current Application are two important papers that I will constantly evaluate and cross-reference to make sure that all requirements are being met for the development of MotorPH. The Project Plan describes the scope of work, dates, and deliverables, while the Application provides as a real-time picture of progress and any potential barriers. I can maintain track of the project's progress and take the required steps to keep it on schedule by closely monitoring these two resources.
8 | Where does the process start? What happens next? | First, visualize and present what the application will look like. Then, design a simple code that: presents employee information in the prescribed format (employee number, employee name, birthday), calculates the number of hours an employee has worked in a week, calculates the gross weekly salary of an employee based on hours worked, and; calculates the net weekly salary of an employee after applying generic deductions.
9 | Where will the results be displayed? | I will adhere to a methodical approach in order to generate the MotorPH application. I will first illustrate their needs, which include gathering employee data, figuring out weekly work hours, figuring out gross weekly pay based on hours worked, and figuring out net weekly pay after deducting expenses. I'll proceed to the next actions as soon as I fully comprehend their requirements: - Week 5: Presentation of employee details - Week 6: Calculation of hours worked - Week 7: Calculation of gross wage - Week 8: Calculation of net wage Following these procedures, I will test and make revisions to the program over Weeks 9 and 10 to make sure it satisfies the specifications and functions as intended. Ultimately, I will turn in the completed product in Week 11.
10 | What details or information do you need to know so you can initiate the task? | When the program is finished, it should produce results in the eleventh week. When that happens, you should expect a thorough results display on the application interface. This will make it simple for you to access and evaluate the data so that it may help you make decisions or take other pertinent activities.
11 | Are there alternative scenarios that you can think of? | Alternative scenarios should be considered to ensure flexibility and preparedness for unexpected developments. 1. Limitations on Resources: - Restricted manpower, equipment, or outside dependencies might affect the schedule. Restrictions can be lessened by finding substitute resources or maximizing those that already exist. 2. Technical Difficulties: - Unexpected technical difficulties, including compatibility problems or complicated data integration, might occur. Plans for backup procedures for diagnosing and fixing these issues should be taken into consideration. 3. Modifications to the Scope: - Requests for additions or modifications from clients throughout development may have an effect on the schedule. Assessing the effect and making the necessary adjustments is crucial. 4. Unexpected Delays: - Delays might be brought on by problems with implementation, testing, or development. It might be wise to modify the schedule or have backup plans. 5. Feedback Iterations from Clients: - Considerable client feedback may cause the development schedule to change. It is essential to communicate on a regular basis and incorporate input effectively. By considering these scenarios, I can adapt the project plan as needed for a successful and timely delivery, emphasizing regular communication and a proactive approach to unforeseen circumstances.
12 | What are the tasks that need to be tracked? | In order to successfully follow the growth of the MotorPH application, I will keep an eye on these tasks: 1. Week 4: Visualizing Requirements: - Task: Produce visual aids that illustrate the client's needs, including employee data, the computation of weekly work hours, the computation of gross weekly compensation, and the determination of net weekly income. 2. Week 5: Employee Details Presentation: - Task: Provide the capability to display employee information in the predetermined format. 3. Week 6: Hours Worked Calculation: - Task: Provide a system that can precisely determine how many hours a worker put in during a certain workweek. 4. Week 7: Gross Wage Calculation: - Task: Provide the mechanism that calculates a worker's gross weekly wage based on hours performed. 5. Week 8: Net Wage Calculation: - Task: After applying the required deductions, compute the net weekly wage by utilizing the deduction application tool. 6. Weeks 9-10: Testing and Revision: - Task: To guarantee functionality and accuracy, carry out extensive testing, find problems, and make the required changes. 7. Week 11: Final Output Submission: - Task: After making sure the application satisfies all standards and has completed successful testing, prepare and submit the final version of the MotorPH application. By keeping an eye on these activities, you can make sure that the development process is managed effectively and that each milestone is reached on schedule.
13 | Do the features indicated by the client meet their current need or solve the problem they're trying to solve? | Yes, the features listed meet the requirements of the client and address the problems they are trying to solve. The development of an all-inclusive payroll and inventory system is purposefully designed to maximize productivity, improve efficiency, and provide better results for clients. This method shows that they have a well-thought-out plan to accomplish their objectives and deal with the difficulties that come with handling goods, personnel information, and compensation during the whole undertaking.

## Estimate
Only access and fill out this sheet when instructed to in your learner guide.
Name |  | Kim Charlotte Anicete
Client Name |  | MotorPH
GUIDE QUESTION | TASK # | RESPONSE
What are the main tasks you need to do? (Insert additional rows if you have more than 10 tasks) | Task 1 | Define MotorPH's requirements
| Task 2 | Illustration of Website Features
| Task 3 | Create an Effort Estimate and a Project Plan
| Task 4 | Structure Code
| Task 5 | Employee Details Presentation
| Task 6 | Calculate Hours Worked and Salary Based on Hours Worked
| Task 7 | Gross and Net Wage Computation
| Task 8 | Testing and Revision
| Task 9 | Conduct Quality Assurance
| Task 10 | Submission of the output
What do you need to know to accomplish these tasks? (Insert additional rows if you have more than 10 tasks) | Task 1 | Know about MotorPH background and data
| Task 2 | How to visualize the features
| Task 3 | Identify the tasks needed and how to divide them
| Task 4 | Know how to structure code
| Task 5 | Gather data of the employee's information and salary
| Task 6 | Know how to calculate Hours Worked and Salary Based on Hours Worked
| Task 7 | Apply government deductions
| Task 8 | Check for errors and defects
| Task 9 | Evaluation from peers/mentor
| Task 10 | How to present the output
What additional help do you think you need to be able to do each task? (Insert additional rows if you have more than 10 tasks) | Task 1 | None
| Task 2 | How to improve the features
| Task 3 | Know the degree of difficulty of each task
| Task 4 | Additional information about structuring code
| Task 5 | None
| Task 6 | Analyzation of the calculation
| Task 7 | Comparison of the Gross and Net Wage computation
| Task 8 | Know how to clear/address errors and defects
| Task 9 | None
| Task 10 | None
Given the nature of the task, the knowledge you need, and any additional help you need, how long do you think it would it take you (in hours) to finish each task? (Insert additional rows if you have more than 10 tasks) | Task 1 | 1 hour
| Task 2 | 2.5 hours
| Task 3 | 2 hour
| Task 4 | 6 hours
| Task 5 | 1 hour
| Task 6 | 8 hours
| Task 7 | 3.5 hours
| Task 8 | 3.5 hours
| Task 9 | 2 hours
| Task 10 | 2 hours
In this course, you are expected to dedicate 7.5 hours per week. Based on the total number of hours you estimated, how many weeks will you need to finish your outputs? | As per the estimated efforts divided per task, the outputs may take four (4) to five (5) weeks to complete. If there may be some delays, these may be accomplished in maximum of six (6) weeks in total.

## Project Plan
Only access and fill out this sheet when instructed to in your learner guide. Use the template below or use any free project management tool available online.
INSTRUCTIONS
Use the guide below to help you fill out this template. TASK # - Use whole numbers to specify main tasks (e.g., 1,2,3). If the task is considered a sub-task, advance the numbering using decimal points to still identify what the main task is (e.g., 1.1, 1.2, 1.3). TASK - Describe the task. Start tasks with verbs/action words to add specificity, e.g., List requirements instead of simply Requirements. DEPENDENCY - Identify the task which cannot be started unless a previous task has been completed. Leave this blank if there is no dependency. OWNER - Identify the person responsible for completing the task. START DATE & END DATE - Identify the planned start and end dates per task. The main task's start and end-date should be the start date of the first sub-task and the end date of the last sub-task. The last end date in your project plan should be within the submission dates indicated in your syllabus. STATUS - By default, all tasks start with a Not Started status. Change the status to In Progress if it's already being worked on and Completed once the task is done. ACTUAL START & END DATE - Specify the actual start and end dates per task. This allows you to identify whether you were able to adhere to your initial timelines and if you will be able to complete the rest of your tasks on time. If you see that you don't have sufficient time, you need to work with your team to decide on alternatives or adjustments. NOTES - Indicate any notes or reminders you may have for each task.
TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
1 | Define MotorPH's requirements |  |  | 2024-01-09 |  | Completed | 2024-01-09 | 2024-01-15
1.1 | Know about MotorPH background and data |  |  |  |  | Completed | 2024-01-09 | 2024-01-09
1.2 | Set assumptions for these requirements | 1.1 |  |  |  | Completed | 2024-01-10 | 2024-01-10
1.3 | Identify the possible outcome and goals | 1.2 |  |  |  | Completed | 2024-01-11 | 2024-01-12
1.4 | Determine the features needed | 1.3 |  |  |  | Completed | 2024-01-12 | 2024-01-13
1.5 | Add or develop features | 1.4 |  |  |  | Completed | 2024-01-15 | 2024-01-15
2 | Illustration of Website Features |  |  |  |  | Completed | 2024-01-18 | 2024-01-22
2.1 | Know about UML Diagrams |  |  |  |  | Completed | 2024-01-18 | 2024-01-18
2.2 | Know about Wireframes |  |  |  |  | Completed | 2024-01-18 | 2024-01-18
2.3 | Know about Use Case Diagram |  |  |  |  | Completed | 2024-01-18 | 2024-01-18
2.4 | Create Use Case Diagram | 2.3 |  |  |  | Completed | 2024-01-19 | 2024-01-20
2.5 | Create Wireframe | 2.2 |  |  |  | Completed | 2024-01-22 | 2024-01-22
3 | Create an Effort Estimate and Project Plan |  |  |  |  | Completed | 2024-01-25 | 2024-01-27
3.1 | Know about Effort Estimation |  |  |  |  | Completed | 2024-01-25 | 2024-01-25
3.2 | Understanding Java Terms |  |  |  |  | Completed | 2024-01-25 | 2024-01-25
3.3 | Know the Variables and Data Types |  |  |  |  | Completed | 2024-01-25 | 2024-01-25
3.4 | Analyze tasks needed and its degree of difficulty | 3.1 |  |  |  | Completed | 2024-01-25 | 2024-01-25
3.5 | Plot all tasks and its needs to accomplish | 3.4 |  |  |  | Completed | 2024-01-26 | 2024-01-27
4 | Structure Code |  |  |  |  | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started